## Info
FYP Project Meeting Minutes
Date | 2011-12-25
Participants
1 | Junaith
2 | Tran Ba Tien
3 | Chang Parkk Khiong Alvin
4 | Phyo Phyo Lwin
5 | Koh Ming Jin
6 | Maung Tin Kyaw Oo
Absent |  | Reasons
Nil

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | DB Design | Changes to DB Design | Tin | Completed | Nil
2 | Coding | More coding to be completed | Team | Completed | Nil
3 | Unit Test | Do more unit Tests | Team | Completed | Nil

## Issues From Last Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Time Report | Everyone to write time report for August, Sep, Oct | Team | Completed | Nil
2 | Workflow Designer front end | Tin finished the workflow designer front end. Alvin's parts (the workflow, steps and formula management) are assigned to Tin. | Maung Tin Kyaw Oo | Completed | Nil
3 | Testing | Testing will involve - unit test: Excel sheet (Tin, Phyo Phyo, Roger, Ba Tien) - integration test (Alvin) - system test: word document (Alvin) - UAT: anyone finished coding will help with UAT script | Team | Completed | Nil
4 | Updating Quality Plan | Alvin to update Quality Plan | Alvin | Completed | Nil
5 | Send email for tasks done | Ba Tien to send out email for everyone about the tasks done in August, Sep and Oct | Tran Ba Tien | Completed | Nil