## Info
FYP Project Meeting Minutes
Date | 2011-05-09
Participants
1 | Maung Tin Kyaw Oo
2 | Tran Ba Tien
3 | Koh Ming Jin
4 | Junaith
5 | Chang Parkk Khiong Alvin
6 | Phyo Phyo Lwin
Absent |  | Reasons
Nil

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | UCRR | Task is assigned for each member to create UCRR during this meeting. | All | Completed | Nil
| UCRR | UC Model Survey & Class Diagram | Tim | Completed | Nil
| UCRR | User Interface Prototype | Tin Kyaw oo | Completed | Nil
| UCRR | UCRRs for Department Manager | Alvin | Completed | Nil
| UCRR | UCRRs for Operation Manager | Roger Koh | Completed | Nil
| UCRR | UCRRs for Worker and Accountant | Phyo Phyo Lwin | Completed | Nil
| UCRR | UCRRs for Sales Staff and Employee | Junaith | Completed | Nil
2 | Class Diagram for UCRR | Tim provided the team with the class diagram necessary for the UCRR. | Tim | Completed | Nil
3 | Designing UCRR on paper first | Alvin suggested that we design the UCRR on paper 1st then combine all at one shot using Rose. | Alvin | Completed | Nil