## Info
FYP Project Meeting Minutes
Date | 2011-07-23
Participants
1 | Maung Tin Kyaw Oo
2 | Tran Ba Tien
3 | Chang Parkk Khiong Alvin
4 | Phyo Phyo Lwin
Absent |  | Reasons
1 | Junaith | Work
2 | Koh Ming Jin | Overseas

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Updates for everyone regarding the client's expectation regarding the GUI for workstation (only 2 actions: update cylinder status and send faulty cylinder). | Update cylinder flow: a. Worker scans cylinder barcode. Remaining steps to be done for cylinder will be shown. (If this is the last step, only 1 step will be shown). b. Choose step to be done. c. Scan employee barcode. - Send faulty cylinder: a. Supervisor scans his employee barcode. b. Enter password. c. Choose 'Cylinder Forwarding' function. d. Scan cylinder barcode. List of steps that has been done will be shown. e. Choose steps to return to. Choose type of error (can be from all departments). Confirm message will be shown. f. Click Confirm. Cylinder status will be changed. | Team | Completed | Nil
2 | Files from Client | Client sent installation files for current production system (3 programs, 3 databases) | Client | Completed | Nil
3 | Architectural decision regarding our system | There will be a web client and a thick client. - Thick client: workflow management with drag and drop. - Web client: all other functions. | Tim | Completed | Nil
4 | Design decision for design UCRRs | Boundary classes: becomes .aspx classes. Each use case will have its own boundary classes - Controller classes: becomes .cs classes. Each use case should use the same set of controller classes from Rose file. - Entity classes: becomes .cs classes. Each use case should use the same set of entity classes. | Team | Completed | Nil
5 | Tasks to be done | 1. Finish Analysis UCRRs 2. Write analysis-design transition document. Write system architecture document. Purchase barcode scanners. Propose to client when to capture start-time and end-time. 3. Write analysis-design transition document. Write system architecture document. Purchase barcode scanners. Propose to client when to capture start-time and end-time. | Team | Completed | Nil