## Info
FYP Project Meeting Minutes
Date | 2011-08-13
Participants
1 | Junaith
2 | Tran Ba Tien
3 | Chang Parkk Khiong Alvin
4 | Phyo Phyo Lwin
5 | Koh Ming Jin
6 | Maung Tin Kyaw Oo
Absent |  | Reasons

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Sat Presentation | The team discussed the tasks to be done for the coming Sat presentation | All | Completed | Nil
2 | Database Design | Tim showed the Team the Database design. The team suggested to Tim that the tables’s names need to be modified. | Tim | Completed | Nil
3 | Minutes for Quality Audit | Alvin did the Minutes for the Quality audit. | Alvin | Completed | Nil
4 | Cover Page | All documents must have same cover page, the pages will be modified by Tim. | Tim | Completed | Nil
5 | Tasks for Presentation | 1. Present Use case – Update Cylinder status 2. Present Use case - Create workflow • Prototype • Project Intro • Gantt Chart (Project Progress) • Printing 6 copies of collaboration diagram • High level architecture (about 3 diagrams, referring Roger’s Prototype report) • Defending the project • Buy Arch lever files | Phyo Alvin Alvin/Phyo Tim Tim Roger Tim Tin Junaith | Completed | Nil