## Info
FYP Project Meeting Minutes
Date | 2011-03-29
Participants
1 | Maung Tin Kyaw Oo
4 | Phyo Phyo Lwin
5 | Tran Ba Tien
Absent |  | Reasons
1 | Chang Parkk Khiong Alvin | Overseas trip
2 | Junaith | Work Commitment
3 | Koh Ming Jin | Work Commitment

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Deliverables | Project Plan, Quality Plan, User Requirement Specs. - Hard copies: hand in during quality audit. - Soft copies: upload to team's folder under Deliverables workbin, SE Project module before Saturday 9th April. | Nil | Completed | -
2 | Quality Audit | We're required to present our project files for quality audit. | All | Completed | On Saturday 2nd April, our team's slot is 9.45 - 10.30am, meeting room S3-2 on the 3rd floor -Assessment criteria are written in attached PPT file.
3 | Presentation | We should address the following: • Introduction to the project (project background etc). • Overview of the user requirements. • Discussion of project risks. • Discussion of technical challenges. • Discussion of your overall project strategies (both management and technical). • Presentation of your projects plans, including estimates and schedule. Your presentation should include a justification for your effort estimates. • Report on overall project progress so far against the plans (planned versus actuals), including a discussion of reasons for differences (if any). • Discussion of management problems that may have occurred during this first phase of the project (such as the need to de-scope, loss of man-power, falling behind schedule etc), including a description of your solutions. | All | Completed | On Saturday 9th April, our team's slot is 10.00 - 10.45 am, classroom 3-3
4 | Peer Assessment Form | Soft copy must be uploaded to our team's folder in the Peer Assessment workbin. | All | Completed | (attached in the email): due by 25th April 2011
5 | Printing and signing final copy | After Tran Ba Tien emails the final copy that needs Maung Tin Kyaw Oo’s signature, Maung Tin Kyaw Oo is to print out and sign it. | Maung Tin Kyaw Oo | Completed | -
6 | Risk Analysis | Work on the risk analysis and send to Tran Ba Tien before Friday | Phyo Phyo Lwin | Completed | -