## Info
FYP Project Meeting Minutes
Date | 2011-04-02
Participants
1 | Maung Tin Kyaw Oo
2 | Tran Ba Tien
3 | Koh Ming Jin
4 | Junaith
Absent |  | Reasons
1 | Chang Parkk Khiong Alvin | Overseas trip
2 | Phyo Phyo Lwin | Went to Hospital

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Quality Audit | Make changes as advised | All | Completed | During the Quality audit on 02 Apr 11 with Dave, he suggested as to make some changes and gave other useful information on our project.
2 | Cover page of Documents | All the Documents must have same type of cover page. | Chang Parkk Khiong Alvin / Tran Ba Tien | Completed | The cover pages are chnged.
3 | Minutes | There must be Minutes for every meeting held. | Junaith | Completed | The Minutes must have full details about the attendees, issues discussed and solutions proposed and actions taken and to be taken.
4 | Roles of Members | Dave asked what the roles of each member are and the task assigned to each person. | Tran Ba Tien | Completed | Individuals are assigned specific task.
5 | View Minutes | Dave took a look at the minutes and suggested that it should also contain the issues discussed last week as well as the Action column. | Junaith | Completed | Nil
6 | Update Project Plan | Dave asked the project Plan to be updated with information using Costar. | Koh Ming Jin | Completed | Nil
7 | Re allocation of work load | The work load of Tran Ba Tien and Maung Tin Kyaw Oo are very high, hence Dave asked the workload to be redistributed across the team. | Tran Ba Tien | Completed | This is to ensure that Tran Ba Tien and Maung Tin Kyaw Oo are not over loaded as well as others also fairly share the work load.
8 | Updating of staff effort estimate | After the work load is redistributed the staff effort estimate must be updated. | Tran Ba Tien | Completed | This is to reflect the estimate of the reallocation of workload for each staff.
9 | Resubmission of (7 and 8) | Dave asked the team to resubmit the above changes (7 and 8) during the presentation on 09 Apr 11. | All | Completed | Dave mentioned that we won’t be penaslised for making these changes.
10 | Documents and Minutes | Dave said that the changes made in any documents must reflect according to the Minutes. | All | Completed | This is to ensure consistency and accuracy.
11 | Delegation of work | Dave mentioned that the dedication of work must be changed in the Quality Plan. | Chang Parkk Khiong Alvin | Completed | Nil
12 | Actual System | The team was asked to bring the actual system for the next meeting. | All | Completed | Nil
13 | Review of previous Minutes | Dave said that the Actions set in the previous Minutes must be reviewed in the next Minute/meeting. | Junaith | Completed | This is to indicate how many hours of work that ach staff has contributed and in what are for that month.
14 | Time sheet | Update Time sheet to indicate the number of hours of each staff’s effort for the month. | All | Completed | Nil
15 | Gantt Chart | Use Gantt chart to keep track control on the Project. | All | Completed | It is better and easier than MS Project.
16 | Situation report | Dave suggested using MS Excel to create and update situation reports. | All | Completed | This to ensure that there is one available for backup work while the other is used for presentation.
17 | Bring 2 laptops | Dave suggested to bring 2 laptops during audit / presentation | All | Completed | Nil
18 | Confirmation to Quality Plan | Dave mentioned that activities and naming convention must confirm to what is written in the Quality Plan. | Chang Parkk Khiong Alvin | Completed | This is to ensure that the team members have reviewed the work and understand the requirements and the changes made.
19 | Internal review | Dave asked if the submittal were reviewed internally before submission and asked for proof of evidence. | All | Completed | The template must have 4 or more columns and must capture details (e.g. DateReviewd, Issue, Suggestion, Reviewer’s Name)
20 | Review Template | For the above mentioned Internal Review there must be templates to fulfil the Review purpose. | Chang Parkk Khiong Alvin | Completed | There must be templates for (Quality Plan, URS, Project Plan)
21 | Remove Work Instruction | Dave asked the Work Instruction to be removed from Quality Plan. | Chang Parkk Khiong Alvin | Completed | Nil
22 | Reflection of Minutes | Dave mentioned that the Minutes must be reflected in the Quality Plan | Chang Parkk Khiong Alvin | Completed | Nil
23 | Changes made must be reflected | Any changes made must be reflected in the relevant documents as well the Minutes | Chang Parkk Khiong Alvin | Completed | Nil
24 | Meeting | Dave suggested the team to have meeting every week. | All | Completed | Nil
25 | Filing system | Dave appreciated the team’s online filing system and said would like to have a look at it in the next meeting. | All | Completed | Nil

## Issues From Last Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Deliverables | Project Plan, Quality Plan, User Requirement Specs. - Hard copies: hand in during quality audit. - Soft copies: upload to team's folder under Deliverables workbin, SE Project module before Saturday 9th April. | Nil | Completed | Nil
2 | Quality Audit | We're required to present our project files for quality audit. | All | Completed | On Saturday 2nd April, our team's slot is 9.45 - 10.30am, meeting room S3-2 on the 3rd floor -Assessment criteria are written in attached PPT file.
3 | Presentation | We should address the following: • Introduction to the project (project background etc). • Overview of the user requirements. • Discussion of project risks. • Discussion of technical challenges. • Discussion of your overall project strategies (both management and technical). • Presentation of your projects plans, including estimates and schedule. Your presentation should include a justification for your effort estimates. • Report on overall project progress so far against the plans (planned versus actuals), including a discussion of reasons for differences (if any). • Discussion of management problems that may have occurred during this first phase of the project (such as the need to de-scope, loss of man-power, falling behind schedule etc), including a description of your solutions. | All | Completed | On Saturday 9th April, our team's slot is 10.00 - 10.45 am, classroom 3-3
4 | Peer Assessment Form | Soft copy must be uploaded to our team's folder in the Peer Assessment workbin. | All | Completed | (attached in the email): due by 25th April 2011
5 | Printing and signing final copy | After Tran Ba Tien emails the final copy that needs Maung Tin Kyaw Oo’s signature, Maung Tin Kyaw Oo is to print out and sign it. | Maung Tin Kyaw Oo | Completed | Nil
6 | Risk Analysis | Work on the risk analysis and send to Tran Ba Tien before Friday | Phyo Phyo Lwin | Completed | Nil