## Info
FYP Project Meeting Minutes
Date | 2011-08-19
Participants
1 | Junaith
2 | Tran Ba Tien
3 | Chang Parkk Khiong Alvin
4 | Phyo Phyo Lwin
5 | Koh Ming Jin
6 | Maung Tin Kyaw Oo
Absent |  | Reasons
Nil

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Purpose of Prototype | Alvin told Roger the Purpose of Prototype: 1. Drag and Drop (work flow relationship) it is working now but initially had difficulties with the even handler. 2. Web Services | Alvin | Completed | Nil
2 | Screenshots of Drag and Drop | Alvin will give Roger screenshots of Drag and Drop | Alvin | Completed | Nil
3 | Prototype study report | Roger confirms with Alvin and Phyo on the Prototype study report | Roger | Completed | Nil
4 | Section 6 for UCRR | Section 6 for UCRR (derived requirements) should be included for all UCRR. | All | Completed | Nil
5 | Boundary Objects | All boundary objects will call MainController. | All | Completed | Nil
6 | UCRR to start at MainPage | Roger makes his UCRR to start at MainPage | Roger | Completed | Nil
7 | Boundary Object to MainPage | Alvin changes boundary object to MainPage | Alvin | Completed | Nil
8 | Pre conditions | Pre conditions will be added into UCRR | All | Completed | Nil
9 | Remove Operations from UCRR. | Alvin will remove operations from UCRR. | Alvin | Completed | Nil
10 | Version Numbering | Version of 3 UCRRs which were peer reviewed for ‘Quality’ will be changed to 1.1 (Please take note that review forms to be created for these files.) | All | Completed | Nil
11 | Prototype data structure | Alvin will send Tin the Prototype data structure | Alvin | Completed | Nil
12 | Multiplicity | Tim’s Class diagram will be used to address multiplicity issues. (Pls follow the Rose file "COMS - Main Workflow v1.7.mdl" for the multiplicity.) | All | Completed | Nil
13 | Review Forms | Everyone who needs to add review forms for their documents are to do so as well. | All | Completed | Nil
14 | Renaming | Rename the wording from "Issue" to "Version" in all UCRR revision table and header. | All | Completed | Nil