## Info
FYP Project Meeting Minutes
Date | 2011-12-31
Participants
1 | Junaith
2 | Tran Ba Tien
3 | Chang Parkk Khiong Alvin
4 | Phyo Phyo Lwin
5 | Koh Ming Jin
6 | Maung Tin Kyaw Oo
Absent |  | Reasons
Nil

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Detailed Design Specs | Update and verify the Detailed Design Specs | Phyo Phyo | Pending | Nil
2 | Source/Executable Code: Tin, Ba Tien and Roger | Do coding | Tin, Ba Tien and Roger | Pending | Nil
3 | Test Documentation | Create the Test documentation | Alvin and Junaith | Pending | Nil
4 | User Guide | Create user gudie in English (TBA) and Vietnamese | Ba Tien | Pending | Nil
5 | End Of Project Report | Create the End Of Project Report | Ba Tien | Pending | Nil

## Issues From Last Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | DB Design | Changes to DB Design | Tin | Completed | Nil
2 | Coding | More coding to be completed | Team | Completed | Nil
3 | Unit Test | Do more unit Tests | Team | Completed | Nil