## Info
FYP Project Meeting Minutes
Date | Thursday, October 27, 2011
Participants
1 | Tran Ba Tien
2 | Chang Parkk Khiong Alvin
3 | Phyo Phyo Lwin
4 | Koh Ming Jin
5 | Maung Tin Kyaw Oo
Absent |  | Reasons
Junaith

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Workflow designer front end | Complete workflow designer front end | Tin | Completed | Nil
2 | Re-assign coding | Take over workflow, step and formula management from Alvin | Tin | Completed | Nil
3 | Test | - Unit Test (Tin, Ba Tien, Roger, Phyo Phyo) - SIT (Alvin, Junaith) - User Trial (Ba Tien) | Everyone | Pending | Nil
4 | Test Documentation | - SIT, User Trial (Alvin, Junaith) | Alvin, Junaith | Pending | Nil
5 | Quality Plan | Update Quality Plan | Alvin | Pending | Nil
6 |  |  |  |  | Nil
7 |  |  |  |  | Nil
8 |  |  |  |  | Nil
9 |  |  |  |  | Nil
10 |  |  |  |  | Nil
11 |  |  |  |  | Nil
12 |  |  |  |  | Nil

## Issues From Last Minutes
S/N | Item | Action Required | Action Party | Status | Remarks