## Info
FYP Project Meeting Minutes
Date | 2011-03-12
Participants
1 | Maung Tin Kyaw Oo
2 | Junaith
3 | Koh Ming Jin
4 | Phyo Phyo Lwin
5 | Tran Ba Tien
Absent |  | Reasons
1 | Chang Parkk Khiong Alvin | Work Commitment

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Process Flow | A sample process flow was drawn on paper and shown to the team members to give an overview of the system | Tran Ba Tien | Completed | Nil
2 | Identification of mock up screen and fileds | Come up with few sample screens and fields | Koh Ming Jin | Completed | Nil

## Issues From Last Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | The Quality Plan was reviewed | Members to suggest and agree to the existing plan or any changes to the plan be made where if necessary. | All | Completed | Contents of quality plan were agreed upon
2 | SVN (Subversion for version control) | Alvin is to set up svn in Google for version control to keep track of changes / versions. | Alvin | Completed | Set up SVN Google
3 | User Representative was changed from Tran Ba Tien to Truong Thieu Duong | NA | Truong Thieu Duong | Completed | Nil
4 | Additional Project Plan Reviwer. Truong Thieu Duong is added as an additional Project Plan Reviwer. | NA | Truong Thieu Duong | Completed | Nil
5 | New Reviewer roles to be assigned to Maung Tin Kyaw Oo: (1) System Specification (2) Enhancement Specification (3) System Test Plan (4) Software Config. Man. Doc. | To be updated in respective documents | Alvin | Completed | Documents updated
10 | Change of role in System Test Plan. Maung Tin Kyaw Oo replaces Alvin Chang as a reviewer for System Test Plan | To be updated in System Test Plan draft | Alvin | Completed | System Test Plan draft updated
11 | Missing templates | To email and ask Dave for the missing templates | Tran Ba Tien | Completed | Templates received from Dave
12 | Bug tracking: Tran Ba Tien suggested to use bug tracker to keep track of bugs and the changes made | To set up bug tracker | Maung Tin Kyaw Oo | Pending
13 | Changes in functional requirement. Some part of the functional requirements were modified | To be updated in user requirements specifications document | Tran Ba Tien | Completed | URS updated