## Info
FYP Project Meeting Minutes
Date | 2011-05-09
Participants
1 | Maung Tin Kyaw Oo
2 | Tran Ba Tien
3 | Koh Ming Jin
4 | Junaith
5 | Chang Parkk Khiong Alvin
6 | Phyo Phyo Lwin
Absent |  | Reasons
Nil

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | UCRR | Task is assigned for each member to create UCRR during this meeting. | All | Completed | Nil
| UCRR | UC Model Survey & Class Diagram | Tim | Completed | Nil
| UCRR | User Interface Prototype | Tin Kyaw oo | Completed | Nil
| UCRR | UCRRs for Department Manager | Alvin | Completed | Nil
| UCRR | UCRRs for Operation Manager | Roger Koh | Completed | Nil
| UCRR | UCRRs for Worker and Accountant | Phyo Phyo Lwin | Completed | Nil
| UCRR | UCRRs for Sales Staff and Employee | Junaith | Completed | Nil
2 | Class Diagram for UCRR | Tim provided the team with the class diagram necessary for the UCRR. | Tim | Completed | Nil
3 | Designing UCRR on paper first | Alvin suggested that we design the UCRR on paper 1st then combine all at one shot using Rose. | Alvin | Completed | Nil

## Issues From Last Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | Scope too big | During the presentation Swarna mentioned that the scope of this project is too big for the team | Tim | Completed | It was mentioned by Swarna during the presentation on 09 Apr 11
2 | Data Migration / Domain Expert | Dave asked about Data migration as well as if we have any any Domain expert for this project | Tim | Completed | It was asked by Dave during the presentation on 09 Apr 11
3 | Analysis | During the presentation Dave asked Tim about Analysis | Tim | Completed | Tim replied that it is done during the Requirement Specifications
4 | Gantt Chart | Dave asked to show Gantt chart | Tim | Completed | Tim will be creating it
5 | Use case modelling | Dave asked if we have started use case modelling. | Tim | Completed | Tim replied that we are behind schedule
6 | Use case modelling survey / programming | Dave asked Tim when can Use case modelling survey and programming be finished | Tim | Completed | Nil
7 | Programming | Dave asked Tim if customer asked him to finish programming early. | Tim | Completed | Tim told Dave that we have realised that we are behind schedule
8 | Integration | Dave asked Tim when will integration be done | Tim |  | Tim replied that it will be done during system testing.
9 | Data migration | Dave asked if everyone is going to do Data migration | NA | NA | Nil
10 | Allocation of tasks | Dave suggested that 4 of us do use case modelling while the other 2 do UI prototyping | All | Completed | Nil
13 | De scoping | Dave and Howard suggested to de scope the project | Tim | Completed | Nil