## Info
FYP Project Meeting Minutes
Date | 2011-06-18
Participants
1 | Maung Tin Kyaw Oo
2 | Tran Ba Tien
3 | Koh Ming Jin
4 | Junaith
5 | Chang Parkk Khiong Alvin
6 | Phyo Phyo Lwin
Absent |  | Reasons
Nil

## Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | MVC or Layer Architecture | The team discussed if to use MVC or layered architecture of the project. | Team | Completed | The advantages and disadvantages of both MVC and Layer Architecture were discussed.
3 | Priority | The worker will be doing the job according to the job’s priority rating. | Tim | Completed | Tim gave the information
4 | Schedules / Work | Schedules will be shown to the worker for him to pick up. Once the barcode of the cylinder is scanned details of the work to be done will be shown to the worker for him to pick up. | Tim | Completed | Tim gave the information
5 | Role Mgt / Workflow Mgt | Alvin clarified if: 1. Role Management is under Admin 2. Workflow Management is under Department Manager | Alvin | Completed | Nil
6 | Display of data | It was discussed that on the same screen different data will be displayed based on the workflow assignment. | Team | Completed | Nil
7 | Diagrams | Diagrams were drawn to illustrate and discuss the work flow and the design of the website | Alvin, Tim | Completed | Nil

## Issues From Last Minutes
S/N | Item | Action Required | Action Party | Status | Remarks
1 | UCRR | Task is assigned for each member to create UCRR during this meeting. | All | Completed | Nil
| UCRR | UC Model Survey & Class Diagram | Tim | Completed | Nil
| UCRR | User Interface Prototype | Tin Kyaw oo | Completed | Nil
| UCRR | UCRRs for Department Manager | Alvin | Completed | Nil
| UCRR | UCRRs for Operation Manager | Roger Koh | Completed | Nil
| UCRR | UCRRs for Worker and Accountant | Phyo Phyo Lwin | Completed | Nil
| UCRR | UCRRs for Sales Staff and Employee | Junaith | Completed | Nil
2 | Class Diagram for UCRR | Tim provided the team with the class diagram necessary for the UCRR. | Tim | Completed | Nil
3 | Designing UCRR on paper first | Alvin suggested that we design the UCRR on paper 1st then combine all at one shot using Rose. | Alvin | Completed | Nil